## Sheet2
MCI Project Weekly Time Sheet
Team | JZ1 | Student ID |  |  | A1902814 | Week starting: | 2025-05-19
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 19 | 10:00 | 14:00 | 4 | Global adjustment of UI color theme | Establish consistent visual style | Tailwind color variables refactored and updated
Tuesday | 20 | 9:00 | 17:00 | 8 | Developed layout and styling for community post page | Initiated new functional page development | First draft completed and shared as UI preview
Wednesday | 21 | 10:00 | 18:00 | 6 | Designed and modularized Register & Login pages | Built core structure of user features | Pages completed and ready for backend integration
Thursday | 22 | 14:00 | 18:00 | 4 | Team meeting to align on components and API format | Clarify frontend-backend integration | API structure confirmed, tasks distributed for testing
Friday | 23 | 14:00 | 20:00 | 6 | Implemented registration form submission with backend | Connected authentication API | Registration & login integration successful and tested
|  |  | Total | 28