## Sheet2
MCI Project Weekly Time Sheet
Team | JZ1 | Student ID |  |  | A1902814 | Week starting: | 2025-03-31
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 31 | 8:00 | 17:00 | 9 | Collate and summarize survey responses | Helps identify key teacher needs to inform platform features and content direction | Highligh ted top concerns and needs of SA K–12 teachers
Tuesday | 1 | 10:00 | 5:00 | 7 | Business Case+Draft Plan(Structure) | Draft core project framing for submission: motivation, goals, and design direction | Drafted initial version of Business Case and structured key goals
Wednesday | 2 | 19:00 | 20:00 | 1 | Meeting with K12 Teachers | Gather qualitative insights to shape case studies and refine survey interpretation | Collected quotes and observations for potential scenario use
Thursday | 3 | 13:00 | 14:00 | 1 | Client Meeting | Align team tasks and progress updates for Milestone 1 submission | Clarified individual responsibilities and timeline
Thursday | 3 | 13:00 | 18:00 | 5 | Business Case+Draft Plan+Milestone(Final) | Finalize Part 1/Part 2 and fill in project milestone structure | Ready-to-submit Business Case with measurable goals and activities
Friday | 4 | 12:00 | 20:00 | 8 | Front-end and back-end construction | Build MVP structure for platform (React + FastAPI) in preparation for future integration | Completed initial layout + backend routing; ready for component work
Saturday | 5
|  |  | Total | 31