## Sheet2
MCI Project Weekly Time Sheet
Team | JZ1 | Student ID |  |  | A1902814 | Week starting: | 2025-04-07
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 7 | 10:00 | 11:00 | 1 | Meeting with Local Student | Gain classroom perspective and feedback from real teaching environment | Noted key points to inspire case study scenario design
Tuesday | 8 | 11:00 | 0:00 | 1 | Group Meeting | Internal check-in on technical progress, case content, and division of upcoming tasks | Set internal deadlines and refined division of labor
Tuesday | 8 | 10:00 | 17:00 | 7 | Front-end and Back-end Construction | Build basic structure of platform MVP (UI + API) | Completed initial layout, login UI, and backend routing logic
Wednesday | 9 | 14:00 | 22:00 | 8 | First case conceptualization | Brainstorm real-world AI use in classroom to guide content module | Outlined scenario theme and learning goals for case 1
Thursday | 10 | 15:00 | 21:00 | 6 | First Case Framework | Start drafting detailed structure of teaching case (background, steps, teacher/student actions) | Completed rough framework of Case 1 for feedback
Friday | 11 | 12:00 | 15:00 | 5 | Front-end Construction | Extend platform components | Built content page template and integrated routing to case detail pages
|  |  | Total | 28