## Sheet2
MCI Project Weekly Time Sheet
Team | JZ1 | Student ID |  |  | A1902814 | Week starting: | 2025-05-05
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 5 | 10:00 | 13:00 | 3 | Reviewed backend API endpoints | Prepare for frontend-backend integration | Documented endpoints and response patterns
Tuesday | 6 | 9:00 | 17:00 | 8 | Refined AI tools UI layout | Improve visual presentation of AI tool cards | Updated grid styling and icons
Wednesday | 7 | 10:00 | 18:00 | 8 | Implemented section transitions | Enhance UI responsiveness and page interaction | Added animation & tested flow logic
Thursday | 8 | 14:00 | 18:00 | 4 | Added loading/error states | Improve user experience while waiting on backend data | States handled for all async fetches
Thursday | 8 | 10:00 | 14:00 | 4 | Adjusted responsive breakpoints | Mobile/tablet optimization for AI tools page | Layout now adapts cleanly on all devices
Friday | 9 | 15:00 | 19:00 | 4 | Client meeting | Sprint retrospective + discuss next milestone | Documented summary & coordinated next task split
|  |  | Total | 31