## Sheet2
MCI Project Weekly Time Sheet
Team | JZ1 | Student ID |  |  | A1902814 | Week starting: | 2025-05-12
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 12 | 9:00 | 12:00 | 3 | Built AI Tools page routing | Link to main nav and section routing | Route integrated successfully
Tuesday | 13 | 9:00 | 17:00 | 8 | Developed teaching case static layout | Start building case page layout | Created structure and base CSS
Wednesday | 14 | 10:00 | 17:00 | 7 | Implemented AI tool functional buttons | Allow interactivity with backend-enabled tools | Buttons functional, state managed
Thursday | 15 | 14:00 | 16:00 | 2 | Group meeting | Review progress & reassign blocked tasks | Discussed backend bugs & synced repo
Thursday | 15 | 19:00 | 22:00 | 3 | Debug | Restore navigation path to AI Tools page | Bug resolved, page now navigable
Friday | 16 | 15:00 | 19:00 | 4 | Basic integration of teaching case data | Prepare teaching case content rendering | Sample case rendered using placeholder JSON
|  |  | Total | 27