## Sheet2
MCI Project Weekly Time Sheet (week10)
Team | JZ1 | Student ID |  | a1833935 |  | Week starting: | 19th May
Day | Date | Time In | Time Out | Total hours | Task | How does it fit ito project plan? | Outcome/Next action
Monday | 2025-05-19 | 10:00 | 15:00 | 5 | Refine UI layout and color | Establish consistent visual style | Finish the UI improvement
Tuesday | 2025-05-20 | 10:00 | 17:00 | 8 | Refine teaching case preview layout | Implement features to meet requirements | Keep working on teaching case preview components
Wednesday | 2025-05-21 | 9:00 | 15:00 | 6 | Develop teaching case preview | Implement features to meet requirements | Keep working on teaching case preview components
Thursday | 2025-05-22 | 13:00 | 18:00 | 5 | Team meeting to align on components and API format | Clarify frontend-backend integration | API structure confirmed, tasks distributed for testing
Friday | 2025-05-23 | 15:00 | 21:00 | 6 | Work on frontend testing | Ensure features can work stably and no errors | Done the test documents
|  |  | Total | 30